## Sheet 1
link | title | summary | author | description | milestone | due_date | labels | assignee
http://172.30.32.3/QCS/QCS-UI/issues/102 | Remove Placement group number from UI | Remove Placement group number from UI | dominic | {} | Milestone 6 | 2018-06-05 | Medium,open | imran.m
http://172.30.32.3/QCS/QCS-UI/issues/112 | Error message as not clear - &#39;Operation failed due to requested entity not fo... | Error message as not clear - 'Operation failed due to requested entity not found' | imran.m | Example:While deleting vm error message throwing as 404. Make the error message user freindly | Milestone 6 | 2018-06-05 | Medium,open | arun.m
http://172.30.32.3/QCS/QCS-UI/issues/42 | OS details has to be added to select os that can be installed later | OS details has to be added to select os that can be installed later | hari.prasad | {} | Milestone 6 | 2018-06-05 | open
http://172.30.32.3/QCS/QCS-UI/issues/69 | In hardware page in detail page remove host/remove disk option is missing | In hardware page in detail page remove host/remove disk option is missing | hari.prasad | {} | Milestone 6 | 2018-06-05 | open | venkatesh.chitluri
http://172.30.32.3/QCS/QCS-API/issues/39 | Storage Pool API | Storage Pool API | dominic | Storage Pool API to Provide, No of Disk, No of Host, No of Vm's, Type of Replication factor - Erasure / Replicated Free, Used and total Capacity | Milestone 6 | 2018-06-05 | Dev-Complete | sundarabalaji.r
http://172.30.32.3/QCS/QCS-UI/issues/145 | Need to display disk level information in All Task section on Storage screen | Need to display disk level information in All Task section on Storage screen | hari.prasad | {} | Milestone 6 | 2018-06-05 | High,open | sundarabalaji.r
http://172.30.32.3/QCS/QCS-UI/issues/70 | Hardware Statistics representation has to be changed | Hardware Statistics representation has to be changed | hari.prasad | {} | Milestone 6 | 2018-06-05 | open | imran.m
http://172.30.32.3/QCS/QCS-UI/issues/156 | Scheduled snapshot for &quot;Daily&quot; has been restricted only for 10 days rather us... | Scheduled snapshot for "Daily" has been restricted only for 10 days rather user should be able to select upto 30 days | fayas Ahamed | ![daily_10_2018-05-25_13-14-49](/uploads/5adc44e9cc91e9029d2e53e94f001323/daily_10_2018-05-25_13-14-49.png) | Milestone 6 | 2018-06-05 | Medium,open | dheeraj.v
http://172.30.32.3/QCS/QCS-UI/issues/131 | Clone,Update and delete buttons are not accessible | Clone,Update and delete buttons are not accessible | fayas Ahamed | unable to access clone,update and delete buttons for certain Vms. ![buttons_2018-05-17_11-13-38](/uploads/c21257f7b74dde87a94181500c504d34/buttons_2018-05-17_11-13-38.png) | Milestone 6 | 2018-06-05 | High,re-open | dominic
http://172.30.32.3/QCS/QCS-UI/issues/118 | In Storage -&gt; VDisk page -&gt; VM name should be shown on tooltip for the corre... | In Storage -> VDisk page -> VM name should be shown on tooltip for the corresponding Disk's | dominic | ![image](/uploads/d902bba4d86df1ffba12485b22322c8c/image.png) | Milestone 6 | 2018-06-05 | High,open | vijayabal.d
http://172.30.32.3/QCS/QCS-UI/issues/130 | Need to modify the Error messages | Need to modify the Error messages | fayas Ahamed | Need to rename some error messages. ![toast_2018-05-15_15-03-21](/uploads/d0815b931f1765dfdf7f737cee140585/toast_2018-05-15_15-03-21.png) Can be modified as: Suggestions: For Vm creation: 1.Vm creation in progress 2.Disk creation in progress 3.Nic creation in progress 4.Vm created successfully For data Provisioned size: ![data_2018-05-15_15-59-59](/uploads/9acccf67114ff8af247f9b545015536a/data_2018-05-15_15-59-59.png) can be modified as "VM Creation failed, due to data memory size is more than maximum". | Milestone 6 | 2018-06-05 | Low,open | arun.m
http://172.30.32.3/QCS/QCS-UI/issues/154 | On Global Task Pull dowm menu - Progress bar does not show appropriate colour... | On Global Task Pull dowm menu - Progress bar does not show appropriate colour indication on VM failure or success scenarios | fayas Ahamed | ![cll_11__2018-05-24_19-57-17](/uploads/7ca743ea77c9b16834605c9ae04dbcba/cll_11__2018-05-24_19-57-17.png) ![cll_2_2018-05-24_19-58-18](/uploads/a092512892d559af0c70c4e8cc90d002/cll_2_2018-05-24_19-58-18.png) | Milestone 6 | 2018-06-05 | High,open | manoj
http://172.30.32.3/QCS/QCS-UI/issues/149 | On VM Info screen -&gt; unable to find the no.of Virtual disk details in &quot;other ... | On VM Info screen -> unable to find the no.of Virtual disk details in "other details " section | fayas Ahamed | fetch the details of "no.of virtual disk" attached to a VM as it's not showing in the "Other details" in "VM details" page. ![new_2d__2018-05-24_15-37-58](/uploads/3807927e6a3685f5e4eb1600c91e217d/new_2d__2018-05-24_15-37-58.png) | Milestone 6 | 2018-06-05 | Medium,open | arun.m
http://172.30.32.3/QCS/QCS-UI/issues/158 | In VM Update - User was able to delete all bootable disk&#39;s | In VM Update - User was able to delete all bootable disk's | fayas Ahamed | 1.Created a VM with one virtual disk and nic successfully 2.After creating VM go to update button and detach the attached bootable disk. 3.After detaching the disk click on cancel button 4.Go to VM details page and select the created VM 5.Go to Vm task of the selected Vm and click on "Virtual disk" tab. 6.Here i can able to see the VM without a minimum Disk. Note: As we already know minimum one disk should be attached to a VM . ![dd_2018-05-25_16-26-51](/uploads/26be59a866ab89d92a74463cc09d7308/dd_2018-05-25_16-26-51.png) ![dd1_2018-05-25_16-27-14](/uploads/0cad0789835d7587093a76643c8eadd5/dd1_2018-05-25_16-27-14.png) | Milestone 6 | 2018-06-05 | High,open | arun.m